## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Fengshou Xu 300036335 | 2024-02-18 | 2024-03-01 | 1 | 0.5
Create <Date> dimension | Fengshou Xu 300036335 | 2024-02-19 | 2024-03-05 | 1 | 0.5
Create <Branch> dimension | Fengshou Xu 300036335 | 2024-02-20 | 2024-03-07 | 1 | 0.5
Create <Customer> dimension | Fengshou Xu 300036335 | 2024-02-21 | 2024-03-08 | 1 | 0.5
Create <Payment> dimension | Fengshou Xu 300036335 | 2024-02-25 | 2024-03-15 | 1 | 0.5
Create <Product> dimension | Guyi Shao 300167461 | 2024-03-01 | 2024-03-07 | 1 | 0.5
Create <Sales_Fact> Fact table | Guyi Shao 300167461 | 2024-03-01 | 2024-03-08 | 1 | 0.5
Staging of dimension <Date> | Hawk Shen 300169700 | 2024-03-01 | 2024-03-09 | 1 | 0.5
Staging of dimension <Branch> | Hawk Shen 300169700 | 2024-03-01 | 2024-03-09 | 1 | 0.5
Staging of dimension <Customer> | Hawk Shen 300169700 | 2024-03-01 | 2024-03-09 | 1 | 0.5
Staging of dimension <Payment> | Hawk Shen 300169700 | 2024-03-02 | 2024-03-09 | 1 | 0.5
Staging of dimension <Product> | Hawk Shen 300169700 | 2024-03-02 | 2024-03-09 | 1 | 0.5
Surrogate key pipeline | Guyi Shao 300167461 | 2024-03-05 | 2024-03-10 | 1 | 0.5
Staging of fact table – including FKs and measures | Guyi Shao 300167461 | 2024-03-05 | 2024-03-10 | 1 | 0.5
Data quality handling and reporting | Guyi Shao 300167461 | 2024-03-07 | 2024-03-14 | 1 | 0.5
Others – if any